## Month 1 - MVP
TASKMATE PRODUCT ROADMAP — MONTH 1: MVP (May 2026)
Goal: Build and internally test the core task management features
Feature Id | Feature Name | Discription | Priority (MoSCoW) | Assigned To | Start Date | End Date | Status
F-01 | User Registration | Sign up and login via email or Google account | Must Have | Dev Team | 2026-05-01 | 2026-05-05 | Planned
F-02 | Task creation | Create a task with title, due date, and priority level | Must Have | Dev Team | 2026-05-05 | 2026-05-10 | Planned
F-03 | Task Dashboard | Home screen showing today's tasks and upcoming deadlines | Must Have | Dev Team+Designer | 2026-05-10 | 2026-05-16 | Planned
F-04 | Push Notification | Send reminder 24 hours before task deadline | Must Have | dev Team | 2026-05-16 | 2026-05-20 | Planned
F-05 | Mark Task Complete | One-tap to mark a task as done and move it to completed list | Must Have | Dev Team | 2026-05-20 | 2026-05-23 | Planned
F-05 | Basic UI Design | Clean and simple interface following Material Design guidelines | Must Have | Designer | 2026-05-01 | 2026-05-15 | Planned
F-07 | Internal Testing (QA) | Test all MVP features on 3 Android devices internally | Must Have | QA Team | 2026-05-24 | 2026-05-31 | Planned

## Month 2 - Beta
TASKMATE PRODUCT ROADMAP — MONTH 2: BETA (June 2026)
Goal: Add secondary features, fix bugs, and launch to 50 beta users
Feature Id | Feature Name | Discription | Priority (MoSCoW) | Assigned To | Start Date | End Date | Status
F-08 | Task Categories | Organize tasks into categories: College, Work, Personal | Should Have | Dev Team | 2026-06-01 | 2026-06-06 | Planned
F-09 | Edit and Delete Tasks | Allow users to modify or remove existing tasks | Must Have | Dev Team | 2026-06-01 | 2026-06-04 | Planned
F-10 | Weekly Planning View | See all tasks organized by day for the full week ahead | Should Have | Dev Team + Designer | 2026-06-06 | 2026-06-12 | Planned
F-11 | Bug Fixes from QA | Resolve all critical and high bugs found in Month 1 testing | Must Have | Dev Team | 2026-06-01 | 2026-06-10 | Planned
F-12 | Beta User Onboarding | Onboard 50 college students as beta testers via Google Form | Should Have | PM+Marketing | 2026-06-12 | 2026-06-18 | Planned
F-13 | Feedback Collection | In-app feedback form + WhatsApp group for beta testers | Should Have | Pm | 2026-06-18 | 2026-06-30 | Planned

## Legend
MOSCOW PRIORITIZATION LEGEND
Color | Priority | Meaning
| Must Have | Non-negotiable. App fails without this.
| Should Have | Important but not critical for launch.
| Could Have | Nice to have if time and budget allow.
(No Fill) | Won't Have | Agreed to exclude from this version.

## Month 3 - Launch
TASKMATE PRODUCT ROADMAP — MONTH 3: LAUNCH (July 2026)
Goal: Fix beta feedback, finalize app, and publish on Google Play Store
Feature Id | Feature Name | Discription | Priority (MoSCoW) | Assigned To | Start Date | End Date | Status
F-14 | Beta Feedback Fixes | Implement top 10 improvements from beta user feedback | Must Have | Dev Team | 2026-07-01 | 2026-07-08 | Planned
F-15 | Weekly Progress Analytics | Show users how many tasks completed vs missed each week | Could Have | Dev Team | 2026-07-01 | 2026-07-08 | Planned
F-16 | Play Store Assets | Create app icon, screenshots, and description for Play Store listing | Must Have | Designer + PM | 2026-07-08 | 2026-07-12 | Planned
F-17 | Final QA Sign-off | Full regression test — confirm crash rate below 1% | Must Have | QA Team | 2026-07-10 | 2026-07-14 | Planned
F-18 | Play Store Submission | Submit app to Google Play Store for review and approval | Must Have | PM + Dev Lead | 2026-07-14 | 2026-07-16 | Planned
F-19 | Launch Marketing | Post on Instagram, LinkedIn, college WhatsApp groups | Should Have | Marketing | 2026-07-16 | 2026-07-20 | Planned
F-20 | Post-Launch Monitoring | Monitor crash reports, ratings, and user reviews daily | Must Have | PM + Dev Team | 2026-07-20 | 2026-07-31 | Planned