## Sheet1
TASKMATE — PROJECT RISK REGISTER
Prepared by: Hrutuja Ingole ¦ Date: 26 April 2026 ¦ Project: TaskMate App Launch
Risk ID | Risk Description | Category | Probability | Impact | Risk Score | Priority | Mitigation Plan | Risk Owner
R-01 | Developer leaves the team mid-project without notice | Resource | Medium | High | 6 | HIGH | Cross-train all developers on each other's modules. Maintain detailed code documentation. | Project Manager
R-02 | Scope creep — stakeholders keep adding new features after development started | Scope | High | High | 9 | CRITICAL | Maintain strict change request process. Features added to next sprint only. | Project Manager
R-03 | App rejected by Google Play Store during submission | Technical | Low | High | 3 | MEDIUM | Review Play Store policies. Conduct compliance checklist 2 weeks before launch. | Lead Developer
R-04 | Low user adoption — fewer than 100 downloads in first 30 days | Market | Medium | High | 6 | HIGH | Begin marketing 4 weeks before launch. Leverage WhatsApp, Instagram, and referrals. | Marketing Lead
R-05 | Critical bug discovered 1 week before launch date | Technical | Medium | High | 6 | HIGH | Full regression testing 2 weeks before launch. Reserve final week strictly for bug fixes. | QA Team
R-06 | Project budget exceeds approved limit of ₹8,00,000 | Financial | Low | High | 3 | MEDIUM | Track expenses weekly. Maintain 10% contingency buffer. PM approves expenses >₹10,000. | Project Manager
R-07 | Push notification feature not working on certain Android versions | Technical | Medium | Medium | 4 | MEDIUM | Test on 5+ Android versions (8.0 to 14). Use Firebase Cloud Messaging. | Lead Developer
R-08 | UI/UX Designer leaves or becomes unavailable during design phase | Resource | Low | Medium | 2 | LOW | Save all design files on shared Figma workspace. PM to have backup access. | Project Manager
R-09 | Poor internet connectivity affecting cloud sync and data saving | Technical | Medium | Medium | 4 | MEDIUM | Add offline task creation in Sprint 2. Store locally, sync when connection restored. | Lead Developer
R-10 | Negative reviews on Play Store in first week due to bugs/poor UX | Market | Low | High | 3 | MEDIUM | Soft launch to 500 users. Monitor reviews daily. Respond to 1-star reviews within 24h. | Marketing + PM
RISK SCORE LEGEND
Risk Score = Probability × Impact
Probability: Low=1, Medium=2, High=3
Impact: Low=1, Medium=2, High=3
SCORE PRIORITY
7-9 → CRITICAL (immediate action required)
5-6 → HIGH (action required this sprint)
3-4 → MEDIUM (monitor closely)
1-2 → LOW (monitor periodically)